## Introduction
Project Name |  |  | PO4_DGELV_DIGITALELEVATOR
Ref Document |  | PO4_DGELV_DIGITALELEVATOR_SRS
Ref Version |  | 1.7
Auther |  | Tarek Sharaby
Last update |  | 23/2/2020
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 27/01/2020 | Initial creation
0.2 | T.Sharaby |  | 2020-07-02 | Update the review with some points
0.3 | T.Sharaby |  | 23/2/2020 | Update the review with some points

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
27/01/2020 | TSH | V1.1 | SRS | 1 | You should manage the status table of the document as follows : Document : xxxxxx Auther : xxxxxx Date : xxxxxx "fo last update " Version : xxxx Status : Darfte , Proposed , Reviewed , Released | Accepted | Resolved
27/01/2020 | TSH | V1.7 | SRS | Revision History | The revision is 1.7 but at the first page it says 1.6 ?! The last modification is at 16 Feb as per history , but in the header it 12 Feb ?! | Accepted | Open |  | Accepted
27/01/2020 | TSH | V1.1 | SRS | ALL | There is no refernce table for the refernce document it should be like this : Ref Docu : xxxxx Version : xxxx Status : xxx Ex the reference for SRS means the input document that enables you to meke the SRS , so the inputs are : - CYRS , and HIS_ if it contains SW req , if not then CYRS is the input for SRS | Accepted | Resolved |  | Refused
27/01/2020 | TSH | V1.7 | SRS | ALL | There is no Software context which decrib the blocks of SW how they are going to communicate in terms of sw features | Accepted | Open
27/01/2020 | TSH | V1.7 | SRS | Software requirement | The goal of the SW req is to descrip what in specific software shall do , so you shall keep the SRS req atmoic means do one thing , and try to make an input and out put for it as much as you can | Accepted | Open |  | Open
27/01/2020 | TSH | V1.1 | SRS | Software requirement | you could represent each req in a table for more organization this table as follows : Req ID : xxx Description : xxxxxx Coverage : the CYRS req Input : xxx if you have it output : if you have | Accepted | Resolved |  | Resolved
27/01/2020 | TSH | V1.1 | SRS | Software requirement | REQ_ PO4_DGELV _SRS_01_V1: for instance this req could be divided in several parts - Software shall accept number of users from 0 to Config_NumbOfUsers , "Config_NumbOfUsers = 10" - when Signal_UserNum is more than Config_NumbOfUsers , the SW shall reject the input and make Signal_ErrorFlag True - etc Here I ttried to consider I have 2 feature in the SW talking with signals : 1- Input acquistion : this get the Signal_UserNum from Keypad as an input and process then give Signal_ErrorFlag as an output 2- Display output: this one will take the Error flag as an input and process it then update the LCD , and so on | Accepted | Resolved
27/01/2020 | TSH | V1.1 | SRS | Software requirement | From what I saw in the req , you are to low level as if you are making SW function not requirement , it is good to dvide the SW into features and then define the information between these feature like I have descriped above , you need to think of the req not the code | Accepted | Resolved
2020-07-02 | TSH | V1.4 | SRS | Software requirement | In the 1st page of the document the verion is 1.6 while status table mention last update was on 6 Feb and version is 1.7 |  | Resolved |  | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
2020-07-02 | TSH | V1.4 | SRS | Software requirement | From what I can see the status is proposed that means there is a cross review has been done and the open points has been considered which is not the case, and if you consider the points then you should of mention that in the history |  | Resolved |  | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open
2020-07-02 | TSH | V1.7 | SRS | Software requirement | There are some SRS req could be divided into 2 or more req |  | Open