## PO4_DGELV_Project_Plan
PROJECT NAME | PROJECT MANAGER | PROJECT START DATE
Digital Elevator [PO4_DGELV] | Ahmed Zoher | 2020-01-21
OVERALL PROGRESS
TASK NAME | FEATURE TYPE | RESPONSIBLE | START DATE | END DATE | ACTUAL START DATE | ACTUAL END DATE | DURATION (DAYS) | TASK STATUS | COMMENTS
Initiation Phase
CYRS Documentation | Non-Technical | Mostafa Sayed - Sara Youssif | 2020-01-21 | 2020-01-22 |  |  |  | Assigned
SRS Documentation | Non-Technical | Mira Zekry - Salma Amr | 2020-01-22 | 2020-01-24 |  |  |  | Assigned
HIS Documentation | Non-Technical | Sara Youssif - Mohamed Nafea | 2020-01-22 | 2020-01-24 |  |  |  | Assigned
RTM Documentation | Non-Technical | Ahmed Zoher | 2020-01-22 | 2020-01-24 |  |  |  | Assigned