## Introduction
Project Name |  |  | PO4_DGELV_DIGITAL ELEVATOR
Ref Document |  | PO4_DGELV_DIGITAL ELEVATOR_CYRS_V1_1
Ref Version |  | 1.1
Auther |  | Tarek Sharaby
Last update |  | 24/01/2020
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 24/01/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
24/01/2020 | T.Sharaby | V1.1 | PO4_DGELV_DIGITAL ELEVATOR_CYRS_V1_1 | Page 1 | Document statuc table : you should put the status of the document which exist in the start in a table , this table holds the following info "Document name , Suther , Version , Auther , Last update Date" |  | Open
24/01/2020 | T.Sharaby | V1.1 | PO4_DGELV_DIGITAL ELEVATOR_CYRS_V1_1 | Revision History | There are 2 revsions with the same version |  | Open |  | Accepted
24/01/2020 | T.Sharaby | V1.1 | PO4_DGELV_DIGITAL ELEVATOR_CYRS_V1_1 | ALL | There is no Reference table to refernce document , even this CYRS is the first Document but you can add the table and refer it is not applicable , and also there is no product context I mean the system blocks from general prospective how they are connected |  | Open |  | Refused
24/01/2020 | T.Sharaby | V1.1 | PO4_DGELV_DIGITAL ELEVATOR_CYRS_V1_1 | ALL | REQ_ PO4_DGELV _CYRS_02_V1_1 : the requirement mention that If the user enter already existing ID system will ask for another , while the REQ_ PO4_DGELV _CYRS_01_V1_1 says each user has a uniques ID so this is duplication |  | Open
24/01/2020 | T.Sharaby | V1.1 | PO4_DGELV_DIGITAL ELEVATOR_CYRS_V1_1 | ALL | REQ_ PO4_DGELV _CYRS_02_V1_1 : this req could be divided into several ones |  | Open |  | Open
24/01/2020 | T.Sharaby | V1.1 | PO4_DGELV_DIGITAL ELEVATOR_CYRS_V1_1 | ALL | REQ_ PO4_DGELV _CYRS_07_V1_1 : why this req is HW as I can see it is SW and what do you mean by movement subsytem should be activated |  | Open |  | Resolved
24/01/2020 | T.Sharaby | V1.1 | PO4_DGELV_DIGITAL ELEVATOR_CYRS_V1_1 | ALL | What is on/off function ? Does it make the system on and off ? If yes then where are these req ? |  | Open
24/01/2020 | T.Sharaby | V1.1 | PO4_DGELV_DIGITAL ELEVATOR_CYRS_V1_1 | Hardware section | Who saied it will 2 button for reset the system ? As it mentioned there is on/off button to make On , off , and Reset |  | Open
24/01/2020 | T.Sharaby | V1.1 | PO4_DGELV_DIGITAL ELEVATOR_CYRS_V1_1 | ALL | I found to documents for the CYRS v1.0 and v1.1 , while we should update only in one document , not every change we will make new document |  | Open |  | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open