## Introduction
Project Name |  |  | PO4_DGELV_DIGITAL ELEVATOR
Ref Document |  | PO4_DGELV_DIGITAL ELEVATOR_HSI
Ref Version |  | 1.3
Auther |  | Tarek Sharaby
Last update |  | 2020-09-02
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 24/01/2020 | Initial creation
0.2 | T.Sharaby |  | 2020-09-02 | Update the status of

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
24/01/2020 | T.Sharaby | V1.0 | PO4_DGELV_DIGITAL ELEVATOR_HSI | Page 1 | Document statuc table : you should put the status of the document which exist in the start in a table , this table holds the following info "Document name , Suther , Version , Auther , Last update Date" | Accepted | Resolved
24/01/2020 | T.Sharaby | V1.0 | PO4_DGELV_DIGITAL ELEVATOR_HSI | ALL | There is no Reference table to refernce document , even this HSI is the first Document but you can add the table and refer it is not applicable | Accepted | Resolved |  | Refused
24/01/2020 | T.Sharaby | V1.0 | PO4_DGELV_DIGITAL ELEVATOR_HSI | ALL | REQ_ PO4_DGELV _HSI_01_V1 : there no mention for the target in specific : Ex : atmega32, also you can add the name of the DC motor and so on I mean at least somehting you can get detailed specs when you search on it | Accepted | Resolved
24/01/2020 | T.Sharaby | V1.0 | PO4_DGELV_DIGITAL ELEVATOR_HSI | ALL | REQ_ PO4_DGELV _HSI_04_V1 : who mention that we will have 2 buttons for on and off and reset ? | Accepted | Resolved |  | Open
24/01/2020 | T.Sharaby | V1.0 | PO4_DGELV_DIGITAL ELEVATOR_HSI | Block Diagram | It should be before the req as it gives global view , it could be better | Accepted | Resolved |  | Resolved
[9 empty] | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open