## PO4_DGELV_Project_Plan
PROJECT NAME | PROJECT MANAGER | PROJECT START DATE
Digital Elevator [PO4_DGELV] | Ahmed Zoher | 2020-01-21
OVERALL PROGRESS
TASK NAME | FEATURE TYPE | RESPONSIBLE | START DATE | END DATE | ACTUAL START DATE | ACTUAL END DATE | DURATION (DAYS) | TASK STATUS | COMMENTS
Week 1
CYRS Documentation | Non-Technical | Mostafa Sayed | 2020-01-21 | 2020-01-22 | 2020-01-24 | 2020-01-24 | 3 | Completed
SRS Documentation | Non-Technical | Mira Zekry | 2020-01-22 | 2020-01-24 | 2020-01-24 | 2020-01-25 | 3 | Completed
HSI Documentation | Non-Technical | Sara Youssif | 2020-01-22 | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2 | Completed
RTM Documentation | Non-Technical | Mohamed Nafea | 2020-01-22 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2 | Completed
HSI Document Review | Non-Technical | Ahmed Zoher | 2020-01-25 | 2020-01-26 | 2020-01-25 | 2020-01-25 | 1 | Completed
CYRS Document Review | Non-Technical | Ahmed Zoher | 2020-01-24 | 2020-01-25 | 2020-01-24 | 2020-01-25 | 1 | Completed
SRS Document Review | Non-Technical | Salma Amr - Mohamed Nafea | 2020-01-25 | 2020-01-26 | 2020-01-25 | 2020-01-25 | 1 | Completed
SRS Document Update | Non-Technical | Salma Amr - Mohamed Nafea | 2020-01-28 | 2020-01-30 | 2020-01-28 | 2020-02-01 | 3 | Completed
Week 2
HSI Document Review | Non-Technical | Sara Youssif | 2020-02-02 | 2020-02-03 |  |  |  | Assigned
CYRS Document Review | Non-Technical | Salma Amr | 2020-02-02 | 2020-02-03 |  |  |  | Assigned
SRS Document Review | Non-Technical | Mira Zekry | 2020-02-04 | 2020-01-05 |  |  |  | Assigned
SRS Document Review | Non-Technical | Mohamed Nafea | 2020-02-05 | 2020-02-06 |  |  |  | Assigned
SRS Document Review | Non-Technical | Mostafa Sayed | 2020-02-06 | 2020-02-07 |  |  |  | Assigned
Overall Documents Review | Non-Technical | Ahmed Zoher | 2020-02-07 | 2020-02-08 |  |  |  | Assigned
SIQ Documents Review | Non-Technical | Ahmed Zoher | 2020-02-07 | 2020-02-08 |  |  |  | Assigned