## PO4_DGELV_Project_Plan
PROJECT NAME | PROJECT MANAGER | PROJECT START DATE
Digital Elevator [PO4_DGELV] | Ahmed Zoher | 2020-01-21
TASK NAME | RESPONSIBLE | START DATE | END DATE | ACTUAL START DATE | ACTUAL END DATE | DURATION (DAYS) | TASK STATUS | COMMENTS
Week 1
CYRS Documentation | Mostafa Sayed | 2020-01-21 | 2020-01-22 | 2020-01-24 | 2020-01-24 | 3 | Completed
SRS Documentation | Mira Zekry | 2020-01-22 | 2020-01-24 | 2020-01-24 | 2020-01-25 | 3 | Completed
HSI Documentation | Sara Youssif | 2020-01-22 | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2 | Completed
RTM Documentation | Mohamed Nafea | 2020-01-22 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2 | Completed
HSI Document Review | Ahmed Zoher | 2020-01-25 | 2020-01-26 | 2020-01-25 | 2020-01-25 | 1 | Completed
CYRS Document Review | Ahmed Zoher | 2020-01-24 | 2020-01-25 | 2020-01-24 | 2020-01-25 | 1 | Completed
SRS Document Review | Salma Amr - Mohamed Nafea | 2020-01-25 | 2020-01-26 | 2020-01-25 | 2020-01-25 | 1 | Completed
SRS Document Update | Salma Amr - Mohamed Nafea | 2020-01-28 | 2020-01-30 | 2020-01-28 | 2020-02-01 | 3 | Completed
Week 2
HSI Document update | Sara Youssif | 2020-02-02 | 2020-02-03 | 2020-02-03 | 2020-02-03 | 1 | Completed
CYRS Document update | Salma Amr | 2020-02-02 | 2020-02-03 | 2020-02-02 | 2020-02-03 | 2 | Completed
SRS Document update | Mira Zekry | 2020-02-04 | 2020-02-05 | 2020-02-05 | 2020-02-05 | 1 | Completed
SRS Document Review and update | Mohamed Nafea | 2020-02-05 | 2020-02-06 | 2020-02-06 | 2020-02-06 | 1 | Completed
SRS Document Review and update | Mostafa Sayed | 2020-02-06 | 2020-02-07 |  |  |  | Assigned
SRS Final Cross Review | Ahmed Zoher | 2020-02-07 | 2020-02-08 |  |  |  | Assigned
CYRS and HIS Final Cross Review | Ahmed Zoher | 2020-02-07 | 2020-02-08 | 2020-02-07 | 2020-02-07 | 1 | Completed
SIQ Document Update | Mostafa Sayed | 2020-02-07 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 1 | Completed
Week 3
HSI Final Update and Review acording to the session's feedback | Sara Youssif | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 1 | Completed
CYRS Final Update and Review acording to the session's feedback | Ahmed Zoher | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 1 | Completed
SRS Update according to session's review and review excel sheet | Mira Zekry | 2020-02-09 | 2020-02-11 | 2020-02-09 | 2020-02-11 | 3 | Completed
SRS cross review and update | Salma Amr | 2020-02-11 | 2020-02-12 | 2020-02-12 | 2020-02-12 | 1 | Completed
RTM and SRS cross review and update | Mohamed Nafea | 2020-02-13 | 2020-02-13 |  |  |  | Assigned
RTM review and update according to finalized SRS, HSI and CYRS | Mostafa Sayed | 2020-02-12 | 2020-02-13 | 2020-02-18 | 2020-02-18 |  | Completed
Week 4
Update SRS according to the review sheet and adding what have been resolved to the SRS review sheet and where exactly the points have been resolved | Mostafa Sayed | 2020-02-22 | 2020-02-23 | 2020-02-22 | 2020-02-26 |  | Assigned
GDD Documentation | Salma Amr | 2020-02-25 | 2020-02-26 |  |  |  | Assigned
GDD Review and adding points to a new review sheet with the same name as the document name | Mira Zekry | 2020-02-26 | 2020-02-26 |  |  |  | Assigned
GDD Update according to the GDD review sheet | Mohamed Nafea | 2020-02-27 | 2020-02-27 |  |  |  | Assigned
Week 5
GDD: Initial Creation + Adding Static Archetecture | Salma Amr | 2020-02-29 | 2020-02-29 |  |  |  | Assigned
GDD: Adding Software Context | Mira Zekry | 2020-03-01 | 2020-03-01 |  |  |  | Assigned
GDD: Adding API Components | Mohamed Nafea | 2020-03-02 | 2020-03-02 |  |  |  | Assigned
GDD: Review | Ahmed Zoher | 2020-03-03 | 2020-03-03 |  |  |  | Assigned
CDD Initial Creation | Mostafa Sayed | 2020-03-03 | 2020-03-05 |  |  |  | Assigned
GDD: Contacting Eng. Tarek for his review | Ahmed Zoher | 2020-03-04 | 2020-03-04 |  |  |  | Assigned
GDD: Update according to the review sheet | Mohamed Nafea | 2020-03-05 | 2020-03-05 |  |  |  | Assigned